## Dashboard
BIOVITAI ¦ V2.1 DELIVERY CONTROL
3 tabs • Modular monolith • AI Gateway • Evidence first • Phase gates
TOTAL TASKS |  | DONE |  | IN PROGRESS |  | BLOCKED
51 |  | 0 |  | 0 |  | 5
ROADMAP PROGRESS BY PHASE
Phase | Weeks | Tasks | Completion |  | MILESTONE GATES
P0 | 1–2 | 7 | 0% |  | M1 | P1 Secure profiles
P1 | 3–5 | 6 | 0% |  | M2 | P3 Health v2
P2 | 6–9 | 5 | 0% |  | M3 | P5 Private pilot
P3 | 10–13 | 5 | 0% |  | M4 | P6 Wellness MVP
P4 | 14–17 | 5 | 0% |  | M5 | P7 Read-only Community
P5 | 18–20 | 4 | 0% |  | M6 | P8 Production rollout
P6 | 21–24 | 9 | 0%
P7 | 25–28 | 5 | 0%
P8 | 29–31 | 5 | 0%
IMPORTANT DELIVERY ASSUMPTIONS
• 31-week phasing is indicative only; no dates or individuals have been committed.
• Tab 1 Health V2 remains intact; Tab 2 Wellness is the core new product; Tab 3 Community is gated.
• Agents use typed domain-service tools. AI Gateway alone calls external model providers.
• Clinical rules, eligibility decisions, consent and data lineage are deterministic and reviewed.
• All 51 tasks begin Backlog. Changing Status in Tasks updates this dashboard.
• The original v2 Markdown files were not present for direct merge; review additive docs 44–59.

## Tasks
ID | Phase | Workstream | Task | Owner Role | Priority | Estimate (days) | Dependencies | Status | Acceptance Criteria | Deliverable | Release Gate | Risk | Description | Notes
BV-001 | P0 | Product | Confirm 3-tab scope and navigation | Product | P0 | 3 |  | In Review | Reviewed navigation spec and user journeys; Tab 3 posting out of MVP | Signed UX scope | P0 | Medium | Freeze 3-tab boundaries and shared assistant behavior | 2026-10-20: Navigation and journeys prepared in docs/p0/REVIEW-PACKET.md; Product/UX signoff pending.
BV-002 | P0 | Architecture | Approve modular-monolith ADR and repository topology | Tech Lead | P0 | 3 | BV-001 | Blocked | ADR accepted; automated module import boundary test planned | ADR-001 | P0 | Medium | Define layered modules and forbidden dependencies | 2026-10-20: BV-001 not approved. Proposed docs/adr/ADR-001-modular-monolith.md and executable import boundary checks prepared; Tech Lead acceptance and DEC-002 pending.
BV-003 | P0 | Privacy | Complete profile and consent threat model | Security/Privacy | P0 | 5 | BV-001 | Blocked | Profile boundary matrix and data flow approved | Threat model | P0 | High | Map identity, family sharing, data processing and tool contexts | 2026-10-20: BV-001 not approved. Draft docs/p0/THREAT-MODEL.md includes access matrix, flow, threats and residual decisions; Security/Privacy approval pending. Owner amendment: specialist signoff deferred for development; see docs/p0/REVIEW-DEFERRAL.md. Engineering acceptance remains required.
BV-004 | P0 | Clinical | Appoint clinical/lab reviewer and define golden-set governance | Product + Clinical | P0 | 3 | BV-001 | Backlog | Named reviewer signoff path, escalation and evidence review method | Clinical governance charter | P0 | High | Medical data and rule review owner | 2026-10-20: Owner deferred specialist reviewer appointment to Backlog for pilot/UAT development. Original acceptance criteria retained; no reviewer appointed. Evidence: docs/p0/REVIEW-DEFERRAL.md.
BV-005 | P0 | Platform | Initialize monorepo, formatter, linting, test runner | Platform | P0 | 4 | BV-002 | Blocked | Fresh install builds; baseline automated checks pass | Monorepo skeleton | P0 | Medium | Developer standards and reproducible environment | 2026-10-20: BV-002 not accepted. Preparatory local npm monorepo/tooling/contracts and CI definition pass 8 tests, lint, format, types and build. Fresh-install evidence in docs/p0/EXECUTION-REPORT.md. No PR/reviewer signoff; no dependency waiver.
BV-006 | P0 | AI | Approve Gateway and agent service contracts | AI Lead | P0 | 3 | BV-002, BV-003 | Blocked | Gateway request/response type and provider abstraction reviewed | ADR-002 / gateway interfaces | P0 | Medium | No direct LLM calls outside gateway | 2026-10-20: BV-002/BV-003 incomplete. Proposed docs/adr/ADR-002-ai-gateway.md and shared/contracts schemas/provider port prepared with negative contract tests; AI Lead/Security review pending; no Gateway implementation. Owner amendment: specialist signoff deferred for development; see docs/p0/REVIEW-DEFERRAL.md. Engineering acceptance remains required.
BV-007 | P0 | Product | Decide target jurisdiction, hosting, languages and minors scope | Product + Legal | P0 | 4 | BV-003 | Blocked | Launch assumptions and legal-review owners documented | Decision log signed | P0 | High | Record DEC-001/006/009 decisions | 2026-10-20: BV-003 incomplete. Recommendations in docs/p0/REVIEW-PACKET.md; DEC-001/006/009 remain Open. Product/Legal decisions and named legal reviewer pending. Owner amendment: specialist signoff deferred for development; see docs/p0/REVIEW-DEFERRAL.md. Engineering acceptance remains required.
BV-008 | P1 | Identity | Implement verified-email auth and sessions | Backend | P0 | 6 | BV-005, BV-003 | Backlog | Invalid sessions rejected; revocation and authentication tests pass | Identity API | P1 | High | Identity foundation and secure session lifecycle
BV-009 | P1 | Identity | Implement family profiles, authorization grants and audit | Backend | P0 | 8 | BV-008, BV-003 | Backlog | Profile A cannot access B via API/worker/cache; revocation test passes | Profile policy service | P1 | High | All profile-scoped access checks
BV-010 | P1 | Data | Create canonical health schema and migrations | Backend + Data | P0 | 7 | BV-005, BV-004 | Backlog | Schema stores comparator, specimen, method, dates and immutable raw field refs | Health migrations | P1 | High | Atomic evidence model and provenance
BV-011 | P1 | Platform | Create object storage, signed access and async job framework | Platform | P0 | 6 | BV-005, BV-003 | Backlog | Private object access; idempotent job demo; replay-safe event | Storage + jobs | P1 | Medium | Upload storage, workers and outbox
BV-012 | P1 | Frontend | Build app shell, tabs, profile switch, auth screens | Frontend | P0 | 7 | BV-001, BV-008 | Backlog | Three tabs usable with feature flags; profile indicator shown | App shell | P1 | Medium | Accessible responsive global navigation
BV-013 | P1 | QA | Set contract and permission integration tests | QA | P0 | 5 | BV-009, BV-010, BV-011 | Backlog | Negative auth tests and schema contract tests run in CI | CI suite | P1 | High | Test harness and CI gating
BV-014 | P2 | Health | Implement report upload and document identity quarantine | Backend | P0 | 7 | BV-009, BV-010, BV-011 | Backlog | Upload belongs to selected profile; mismatched identity quarantined | Upload API | P2 | High | Multi-page upload, scanning, metadata and ownership
BV-015 | P2 | Health | Build OCR adapter and layout-aware extraction pipeline | AI/Backend | P0 | 10 | BV-014, BV-006 | Backlog | Every field has source page/region where feasible; extraction version tracked | Extraction worker | P2 | High | Page/box provenance and table relationships
BV-016 | P2 | Health | Build human verification/correction UI | Frontend | P0 | 7 | BV-015, BV-012 | Backlog | Correction history preserved, uncertain fields require review | Verification screen | P2 | High | Confirm raw value/unit/interval/date before publication
BV-017 | P2 | Health | Implement source observation storage and status changes | Backend | P0 | 6 | BV-010, BV-015 | Backlog | No source field overwritten by derived value; auditable versioning | Observation repository | P2 | High | Raw vs verified data boundary
BV-018 | P2 | QA | Build 50+ synthetic clinical extraction golden cases | QA + Clinical | P0 | 6 | BV-015, BV-004 | Backlog | Expected raw field exact matches, identity conflict and failure states covered | Extraction goldens | P2 | High | Diverse source variants, censored and corrected
BV-019 | P3 | Clinical | Implement comparability cohorts and controlled aggregation | Health + Clinical | P0 | 10 | BV-017, BV-018 | Backlog | Zero known false merges on goldens; full provenance for derived values | Comparability service | P3 | High | No averaging distinct lab results; provenance lineage
BV-020 | P3 | Health | Implement versioned longitudinal biomarker trends | Backend | P0 | 8 | BV-019 | Backlog | Time/specimen/method and comparators respected; corrections invalidate cache | Trend API | P3 | High | Comparable, qualified trend histories
BV-021 | P3 | Frontend | Create health dashboard and report evidence drilldowns | Frontend | P1 | 10 | BV-016, BV-020 | Backlog | Every displayed value has evidence link; no generic organ health score | Health UI | P3 | Medium | Body map with verified vs not-assessed labels
BV-022 | P3 | Health | Implement cross-report comparison service | Backend | P0 | 7 | BV-019, BV-020 | Backlog | Comparison excludes noncomparable results and cites both documents | Comparison API | P3 | High | Safe marker matching, source differences
BV-023 | P3 | QA | Validate clinical interpretations and provenance UX | QA + Clinical | P0 | 7 | BV-021, BV-022 | Backlog | Goldens pass; ambiguities shown; source correction propagation tested | P3 clinical gate | P3 | High | Clinical signoff on report and comparison goldens
BV-024 | P4 | AI | Implement provider-neutral AI Gateway | AI/Platform | P0 | 9 | BV-006, BV-005 | Backlog | All SDK use isolated; schema invalid output fails safely; budgets observed | AI Gateway | P4 | High | Policy, routing, minimization, schema, token budget
BV-025 | P4 | AI | Implement permission-checked tool registry and adapters | AI/Backend | P0 | 9 | BV-009, BV-022, BV-024 | Backlog | Tool allowlist enforced; profile isolation and timeout pass | AI tools | P4 | High | Tools call health/wellness domain services, never database
BV-026 | P4 | AI | Build context manifest and conversation orchestrator | AI | P0 | 8 | BV-025 | Backlog | Relevant evidence retrieved without full raw report leakage | Orchestrator | P4 | High | Filtered health context + tool plan
BV-027 | P4 | Frontend | Build structured chat UI cards and citations | Frontend | P1 | 8 | BV-026, BV-012 | Backlog | Rendering rejects arbitrary HTML and supports RTL/citations | AI chat UI | P4 | Medium | Schema-validated components, accessible
BV-028 | P4 | Security | Run AI injection/PHI and provider regression suite | QA + Security | P0 | 7 | BV-026, BV-027 | Backlog | All high-severity prompt injection/citation cases pass | AI safety gate | P4 | High | Cross-profile, malicious PDF/post, fabricated source
BV-029 | P5 | Pilot | Create consented pilot protocol and qualitative interview plan | Product + Clinical | P0 | 4 | BV-023, BV-028 | Backlog | Privacy, success criteria, participant rights documented | Pilot protocol | P5 | High | Family pilot with safe synthetic/matched reports
BV-030 | P5 | QA | E2E user journeys and accessibility/l10n audit | QA + UX | P0 | 8 | BV-029 | Backlog | Critical journeys pass; WCAG and Arabic/English defects triaged | E2E report | P5 | Medium | Upload→verify→trend→chat; switching family
BV-031 | P5 | Platform | Instrument production-like observability and back-up restore | Platform | P0 | 6 | BV-024, BV-011 | Backlog | Trace across worker/gateway; restore tested | Pilot ops gate | P5 | High | PHI-safe telemetry, error budgets, restore drill
BV-032 | P5 | Pilot | Run controlled health + AI pilot and address defects | Product + QA | P0 | 10 | BV-030, BV-031 | Backlog | Pilot signoff and prioritized issues recorded | M3 pilot report | P5 | High | No open severity-1/2 privacy or clinical defects
BV-033 | P6 | Wellness | Implement wellness profile, baseline and goal selection | Wellness | P0 | 7 | BV-009, BV-012, BV-032 | Backlog | Can start without labs/wearables; goals opt-in and editable | Wellness profile/goal | P6 | Medium | Voluntary barriers/readiness and context
BV-034 | P6 | Clinical | Approve action catalogue and eligibility policies | Clinical + Behavior | P0 | 10 | BV-004, BV-033 | Backlog | Every surfaced action reviewed and reason-traceable | Action catalogue | P6 | High | Reviewed micro-actions, exclusions, locales and versions
BV-035 | P6 | Wellness | Implement plan engine and user-selected variants | Backend | P0 | 8 | BV-033, BV-034 | Backlog | No action from LLM free text; user selection required | Plan Engine | P6 | High | Minimum/normal/fallback action service
BV-036 | P6 | Wellness | Implement check-ins, barrier and recovery flow | Frontend + Backend | P0 | 10 | BV-035 | Backlog | Missed app opens ≠ failed habit; recovery history persists | Recovery UX/service | P6 | Medium | No punitive reset; preserved achievements
BV-037 | P6 | AI | Add authorized Wellness Coach tools and cards | AI | P1 | 6 | BV-035, BV-026 | Backlog | No unreviewed plan generation; tool calls scoped | Wellness AI | P6 | High | Gateway explanation of deterministic decisions
BV-038 | P6 | Devices | Implement manual vitals/device integration adapter | Integration | P1 | 8 | BV-033, BV-010 | Backlog | Manual works; device revocation and duplicate policy tested | Device adapter | P6 | Medium | Device optional; provenance/data gaps distinguished
BV-039 | P6 | Wellness | Implement preference-driven reminders and burden budget | Wellness | P1 | 6 | BV-036 | Backlog | No nagging after pause; reminder caps proven | Notifications | P6 | Medium | Quiet hours, opt-in, consent change handling
BV-040 | P6 | Analytics | Instrument sustained behavior and equity metrics | Product Analytics | P0 | 6 | BV-036, BV-038 | Backlog | Outcome definitions and denominators approved before pilot | Wellness metrics | P6 | Medium | 3/6/12 mo cohort, recovery time, missingness
BV-041 | P6 | QA | Run wellness safety, accessibility and adaptation goldens | QA + Clinical | P0 | 9 | BV-036, BV-037, BV-039, BV-040 | Backlog | No unsafe action; non-shaming recovery; locale and opt-out pass | M4 wellness pilot gate | P6 | High | Heat, shift, Ramadan opt-in, mobility, illness cases
BV-042 | P7 | Community | Define reviewed source and content-label schema | Community | P1 | 5 | BV-001, BV-003 | Backlog | Source classifications and expiration/review requirements defined | Content model | P7 | Medium | Authority level, publish date, credential policy
BV-043 | P7 | Community | Build curated read-only Community feed | Frontend + Backend | P1 | 8 | BV-042, BV-012 | Backlog | Public feed independent of Health; articles cite sources | Read-only Community | P7 | Medium | Source-linked news/posts and search
BV-044 | P7 | Trust/Safety | Implement content submission + moderation queue behind flag | Trust & Safety | P2 | 10 | BV-043, BV-024 | Backlog | Posts remain unpublished until policy gate; appeals auditable | Moderation beta | P7 | High | Reports, bans, privacy prompts and appeals
BV-045 | P7 | Security | Pen-test Community-to-Health/AI trust boundary | Security + QA | P0 | 7 | BV-044, BV-025 | Backlog | Cannot access clinical context or agent tools via posts | Community isolation gate | P7 | High | UGC prompt injection and data exfiltration
BV-046 | P7 | Product | Approve community posting launch separately | Product + Legal | P2 | 4 | BV-044, BV-045 | Backlog | Posting remains OFF unless independent gate signed | Community go/no-go | P7 | High | Staff moderation, policies, legal check
BV-047 | P8 | Security | Conduct external security/privacy assessment | Security + Legal | P0 | 8 | BV-032, BV-041 | Backlog | No critical unremediated security findings | Security signoff | P8 | High | Authz, encryption, cross-border processing, logging
BV-048 | P8 | Platform | Test rollback, disaster recovery and SLO alerting | Platform | P0 | 7 | BV-031, BV-047 | Backlog | Chaos/recovery drill and rollback accepted | Ops signoff | P8 | High | Canary, incident runbook, backup restore
BV-049 | P8 | Accessibility | Complete localization, RTL and accessibility audit | UX + QA | P0 | 7 | BV-041, BV-043 | Backlog | Priority accessibility defects closed | Accessibility signoff | P8 | Medium | Core en/ar UI and measured accessibility
BV-050 | P8 | Legal/Clinical | Approve jurisdiction, product claims and clinical disclaimers | Legal + Clinical | P0 | 7 | BV-047, BV-049 | Backlog | Regulatory approach and product claims signed | Compliance signoff | P8 | High | Formal legal/clinical review of actual deployment
BV-051 | P8 | Launch | Controlled rollout with feature flags and kill switches | Product + Platform | P0 | 5 | BV-048, BV-050 | Backlog | All gates complete, staged rollout and rollback ready | M6 launch | P8 | High | Go/no-go and monitoring launch

## Phases
Phase | Name | Start Week | End Week | Duration (weeks) | Scope | Task Count | Critical P0 | Gate | Status | Completion %
P0 | Foundation | 1 | 2 | 2 | Architecture, clinical governance, privacy & dev tooling | 7 | 7 | P0 | Blocked | 0%
P1 | Platform & Identity | 3 | 5 | 3 | Profile auth, authorization, canonical data | 6 | 6 | P1 | Not Started | 0%
P2 | Medical Reports | 6 | 9 | 4 | Upload, OCR, verification & raw observation | 5 | 5 | P2 | Not Started | 0%
P3 | Health Intelligence | 10 | 13 | 4 | Safe aggregation, trends, body view | 5 | 4 | P3 | Not Started | 0%
P4 | AI Platform | 14 | 17 | 4 | AI Gateway, tools, chat | 5 | 4 | P4 | Not Started | 0%
P5 | Private Pilot | 18 | 20 | 3 | Privacy/clinical pilot, instrumentation | 4 | 4 | P5 | Not Started | 0%
P6 | Adaptive Wellness | 21 | 24 | 4 | Reviewed actions, plan, recovery, device data | 9 | 6 | P6 | Not Started | 0%
P7 | Community Beta | 25 | 28 | 4 | Curated feed; moderated posting optional | 5 | 1 | P7 | Not Started | 0%
P8 | Production Readiness | 29 | 31 | 3 | Security, legal, operations, rollout | 5 | 5 | P8 | Not Started | 0%

## Decisions
ID | Decision | Owner Role | Due Gate | Status | Notes
DEC-001 | Launch jurisdiction and health-data hosting region | Product + Legal | P0 | Open | Do not assume regulatory approval
DEC-002 | Frontend/mobile stack and deployment platform | Tech Lead | P0 | Open | Favor typed contracts and monorepo
DEC-003 | OCR vendor and supported lab templates | AI Lead + Clinical | P2 | Open | Measure on representative reports
DEC-004 | Named clinical/lab rule reviewer | Product | P0 | Open | Independent review before pilot
DEC-005 | AI model provider and fallback | AI Lead + Security | P4 | Open | Residency and safety eval
DEC-006 | English/Arabic and additional languages | Product + UX | P0 | Open | RTL tests mandatory
DEC-007 | Wearables and authorization vendors | Integrations | P6 | Open | Manual input first
DEC-008 | Community posting launch policy | Trust & Safety | P7 | Open | Posting feature flagged off
DEC-009 | Minors / family guardianship | Legal + Privacy | P1 | Open | No minors until approved
DEC-010 | 3/6/12 month wellness cohort design | Product Analytics | P6 | Open | Not an early pilot success claim

## Dependencies
Prerequisite Task | Blocked Task | Downstream Work | Phase | Priority
BV-001 | BV-002 | Approve modular-monolith ADR and repository topology | P0 | P0
BV-001 | BV-003 | Complete profile and consent threat model | P0 | P0
BV-001 | BV-004 | Appoint clinical/lab reviewer and define golden-set governance | P0 | P0
BV-002 | BV-005 | Initialize monorepo, formatter, linting, test runner | P0 | P0
BV-002 | BV-006 | Approve Gateway and agent service contracts | P0 | P0
BV-003 | BV-006 | Approve Gateway and agent service contracts | P0 | P0
BV-003 | BV-007 | Decide target jurisdiction, hosting, languages and minors scope | P0 | P0
BV-005 | BV-008 | Implement verified-email auth and sessions | P1 | P0
BV-003 | BV-008 | Implement verified-email auth and sessions | P1 | P0
BV-008 | BV-009 | Implement family profiles, authorization grants and audit | P1 | P0
BV-003 | BV-009 | Implement family profiles, authorization grants and audit | P1 | P0
BV-005 | BV-010 | Create canonical health schema and migrations | P1 | P0
BV-004 | BV-010 | Create canonical health schema and migrations | P1 | P0
BV-005 | BV-011 | Create object storage, signed access and async job framework | P1 | P0
BV-003 | BV-011 | Create object storage, signed access and async job framework | P1 | P0
BV-001 | BV-012 | Build app shell, tabs, profile switch, auth screens | P1 | P0
BV-008 | BV-012 | Build app shell, tabs, profile switch, auth screens | P1 | P0
BV-009 | BV-013 | Set contract and permission integration tests | P1 | P0
BV-010 | BV-013 | Set contract and permission integration tests | P1 | P0
BV-011 | BV-013 | Set contract and permission integration tests | P1 | P0
BV-009 | BV-014 | Implement report upload and document identity quarantine | P2 | P0
BV-010 | BV-014 | Implement report upload and document identity quarantine | P2 | P0
BV-011 | BV-014 | Implement report upload and document identity quarantine | P2 | P0
BV-014 | BV-015 | Build OCR adapter and layout-aware extraction pipeline | P2 | P0
BV-006 | BV-015 | Build OCR adapter and layout-aware extraction pipeline | P2 | P0
BV-015 | BV-016 | Build human verification/correction UI | P2 | P0
BV-012 | BV-016 | Build human verification/correction UI | P2 | P0
BV-010 | BV-017 | Implement source observation storage and status changes | P2 | P0
BV-015 | BV-017 | Implement source observation storage and status changes | P2 | P0
BV-015 | BV-018 | Build 50+ synthetic clinical extraction golden cases | P2 | P0
BV-004 | BV-018 | Build 50+ synthetic clinical extraction golden cases | P2 | P0
BV-017 | BV-019 | Implement comparability cohorts and controlled aggregation | P3 | P0
BV-018 | BV-019 | Implement comparability cohorts and controlled aggregation | P3 | P0
BV-019 | BV-020 | Implement versioned longitudinal biomarker trends | P3 | P0
BV-016 | BV-021 | Create health dashboard and report evidence drilldowns | P3 | P1
BV-020 | BV-021 | Create health dashboard and report evidence drilldowns | P3 | P1
BV-019 | BV-022 | Implement cross-report comparison service | P3 | P0
BV-020 | BV-022 | Implement cross-report comparison service | P3 | P0
BV-021 | BV-023 | Validate clinical interpretations and provenance UX | P3 | P0
BV-022 | BV-023 | Validate clinical interpretations and provenance UX | P3 | P0
BV-006 | BV-024 | Implement provider-neutral AI Gateway | P4 | P0
BV-005 | BV-024 | Implement provider-neutral AI Gateway | P4 | P0
BV-009 | BV-025 | Implement permission-checked tool registry and adapters | P4 | P0
BV-022 | BV-025 | Implement permission-checked tool registry and adapters | P4 | P0
BV-024 | BV-025 | Implement permission-checked tool registry and adapters | P4 | P0
BV-025 | BV-026 | Build context manifest and conversation orchestrator | P4 | P0
BV-026 | BV-027 | Build structured chat UI cards and citations | P4 | P1
BV-012 | BV-027 | Build structured chat UI cards and citations | P4 | P1
BV-026 | BV-028 | Run AI injection/PHI and provider regression suite | P4 | P0
BV-027 | BV-028 | Run AI injection/PHI and provider regression suite | P4 | P0
BV-023 | BV-029 | Create consented pilot protocol and qualitative interview plan | P5 | P0
BV-028 | BV-029 | Create consented pilot protocol and qualitative interview plan | P5 | P0
BV-029 | BV-030 | E2E user journeys and accessibility/l10n audit | P5 | P0
BV-024 | BV-031 | Instrument production-like observability and back-up restore | P5 | P0
BV-011 | BV-031 | Instrument production-like observability and back-up restore | P5 | P0
BV-030 | BV-032 | Run controlled health + AI pilot and address defects | P5 | P0
BV-031 | BV-032 | Run controlled health + AI pilot and address defects | P5 | P0
BV-009 | BV-033 | Implement wellness profile, baseline and goal selection | P6 | P0
BV-012 | BV-033 | Implement wellness profile, baseline and goal selection | P6 | P0
BV-032 | BV-033 | Implement wellness profile, baseline and goal selection | P6 | P0
BV-004 | BV-034 | Approve action catalogue and eligibility policies | P6 | P0
BV-033 | BV-034 | Approve action catalogue and eligibility policies | P6 | P0
BV-033 | BV-035 | Implement plan engine and user-selected variants | P6 | P0
BV-034 | BV-035 | Implement plan engine and user-selected variants | P6 | P0
BV-035 | BV-036 | Implement check-ins, barrier and recovery flow | P6 | P0
BV-035 | BV-037 | Add authorized Wellness Coach tools and cards | P6 | P1
BV-026 | BV-037 | Add authorized Wellness Coach tools and cards | P6 | P1
BV-033 | BV-038 | Implement manual vitals/device integration adapter | P6 | P1
BV-010 | BV-038 | Implement manual vitals/device integration adapter | P6 | P1
BV-036 | BV-039 | Implement preference-driven reminders and burden budget | P6 | P1
BV-036 | BV-040 | Instrument sustained behavior and equity metrics | P6 | P0
BV-038 | BV-040 | Instrument sustained behavior and equity metrics | P6 | P0
BV-036 | BV-041 | Run wellness safety, accessibility and adaptation goldens | P6 | P0
BV-037 | BV-041 | Run wellness safety, accessibility and adaptation goldens | P6 | P0
BV-039 | BV-041 | Run wellness safety, accessibility and adaptation goldens | P6 | P0
BV-040 | BV-041 | Run wellness safety, accessibility and adaptation goldens | P6 | P0
BV-001 | BV-042 | Define reviewed source and content-label schema | P7 | P1
BV-003 | BV-042 | Define reviewed source and content-label schema | P7 | P1
BV-042 | BV-043 | Build curated read-only Community feed | P7 | P1
BV-012 | BV-043 | Build curated read-only Community feed | P7 | P1
BV-043 | BV-044 | Implement content submission + moderation queue behind flag | P7 | P2
BV-024 | BV-044 | Implement content submission + moderation queue behind flag | P7 | P2
BV-044 | BV-045 | Pen-test Community-to-Health/AI trust boundary | P7 | P0
BV-025 | BV-045 | Pen-test Community-to-Health/AI trust boundary | P7 | P0
BV-044 | BV-046 | Approve community posting launch separately | P7 | P2
BV-045 | BV-046 | Approve community posting launch separately | P7 | P2
BV-032 | BV-047 | Conduct external security/privacy assessment | P8 | P0
BV-041 | BV-047 | Conduct external security/privacy assessment | P8 | P0
BV-031 | BV-048 | Test rollback, disaster recovery and SLO alerting | P8 | P0
BV-047 | BV-048 | Test rollback, disaster recovery and SLO alerting | P8 | P0
BV-041 | BV-049 | Complete localization, RTL and accessibility audit | P8 | P0
BV-043 | BV-049 | Complete localization, RTL and accessibility audit | P8 | P0
BV-047 | BV-050 | Approve jurisdiction, product claims and clinical disclaimers | P8 | P0
BV-049 | BV-050 | Approve jurisdiction, product claims and clinical disclaimers | P8 | P0
BV-048 | BV-051 | Controlled rollout with feature flags and kill switches | P8 | P0
BV-050 | BV-051 | Controlled rollout with feature flags and kill switches | P8 | P0